## Sheet1
Name | Duration
Develop objectives | 4d
Identify attendees | 3d
Develop budget | 7d
Plan theme | 2d
Plan schedule | 5d
Choose possible sites | 2d
Send Request for proposals to sites | 2d
Set up tour of offsite venue | 14d
Conduct site survey | 1d
Visit offsite venue/sign contract | 3d
Choose main venue/sign hotel contract | 2d
Put together info for kickoff meeting | 4d
Kickoff meeting/additional job assignments | 0d
Develop meeting content | 7d
Contract with Speakers | 14d
Develop marketing materials | 7d
Order/receive initial marketing materials | 35d
Update website with event details | 1d
Registration materials/web registration setup | 9d
Marketing materials mailed/emailed out | 4d
Registration starts | 0d
Travel arrangements made for staff and speakers | 60d
Sleeping rooms reserved for staff and speakers | 2d
Food and Beverage selections | 4d
Food and Beverage for off site location | 3d
AV Needs | 7d
Establish meeting room needs | 8d
Develop room layout | 6d
Develop event décor and contract 3rd party vendors | 14d
Develop evaluations | 10d
Order supplies | 7d
Order gift bags | 21d
Verify count for hotel events | 2d
Verify count for off site event | 2d
Update website with any last minute details | 8d
Update any meeting room needs | 3d
Name tags and packets done | 5d
Ship materials as necessary | 7d
Make event specification guide | 7d
Travel day | 1d
Pre-conference staff meeting with hotel staff | 0d
Setup starts | 1d
Speakers dinner | 0d
Setup finished | 1d
Meet with off site location for final instructions | 1d
Gift bags placed in room for guest arrival | 1d
Meeting Day | 0d
Evaluations | 1d
Post conference meeting with various groups | 1d
Review Bill | 1d
Pay Bill | 0d
Evaluations sent again | 2d
ROI report compiled | 7d
Report on success of meeting | 0d