## Slide 1: Project Risk Management

## Slide 2: Learning Objectives
Understand what risk is and the importance of good project risk management.
Identify project risks, describe the risk identification process, tools and techniques to help identify project risks
Determine quantitative or qualitative value of project risks and prioritize them in a risk management plan
Propose plans to mitigate such risks, risk register
Monitor and control the risks
Manage projects by lowering internal and external risks

## Slide 3: Learning Objectives (cont’d)
Explain the quantitative risk analysis process and how to apply decision trees, simulation, and sensitivity analysis to quantify risks.
Provide examples of using different risk response planning strategies to address both negative and positive risks.
Discuss what is involved in risk monitoring and control.
Describe how software can assist in project risk management.

## Slide 4: The Importance of Project Risk Management
Project risk management is the art and science of identifying, analyzing, and responding to risk throughout the life of a project and in the best interests of meeting project objectives.
Risk management is often overlooked in projects, but it can help improve project success by helping select good projects, determining project scope, and developing realistic estimates.

## Slide 5: Benefits from Software Risk Management Practices*
*Kulik, Peter and Catherine Weber, “Software Risk Management Practices – 2001,” KLCI Research Group (August 2001).

## Slide 6: PMBOK MAPPING TO RISK MGMT

## Slide 7: INTEGRATING RISK
PROJECT
MANAGEMENT
INTEGRATION
SCOPE
QUALITY
TIME
COST
HUMAN
RESOURCES
CONTRACT /
PROCUREMENT
INFORMATION /
COMMUNICATIONS
PROJECT
RISK
Life Cycle and
Environment Variables
Services, Plant, Materials:
Performance
Cost Objectives,
Restraints
Restraints
Expectations
Feasibility
Ideas, Directives,
Data Exchange Accuracy
Requirements
Standards
Availability
Productivity
Time Objectives,
Ref: Project and Program Risk Management, Wideman
Notes: THIS FIGURE SHOWS HOW RISK MGT IS INEXTRICABLY TIED TO
THE REMAINING 7 PMBOK MANAGEMENT FUNCTIONS. NOTE
HOW SPECIFIC AREAS OF RISK ARE ASSOCIATED WITH EACH
OF THE INDIVIDUAL FUNCTIONS AS SHOWN ON THE DIAGRAM.
TALK TO THE VARIOUS FUNCTIONS AND GIVE EXAMPLES. <-NEXT PAGE
EXPERIENCE ON MANY PROJECTS REVEALS POOR PERFORMANCE
IN TERMS OF REACHING SCOPE, QUALITY, TIME, AND COST
OBJECTIVES. MANY OF THESE SHORTCOMINGS ARE
ATTRIBUTED EITHER TO UNFORESEEN EVENTS, WHICH MIGHT
OR MIGHT NOT HAVE BEEN ANTICIPATED BY MORE EXPERIENCED
PROJECT MANAGEMENT, OR TO FORESEEN EVENTS FOR
WHICH THE RISKS WERE NOT FULLY ACCOMMODATED.
** BETTER DECISIONS VIA RISK MGMT APPROACH VS. SEAT OF PANTS
ONE OF THE BIGGEST HURDLES IS THAT OF MANAGEMENT'S
ATTITUDE TO RISK ITSELF. SOME HAVE LITTLE UNDERSTANDING
OF THE CONCEPTS, WHILE OTHERS LACK CONFIDENCE IN
THE MATHEMATICAL TECHNIQUES AND RESULTS OBTAINED,
PREFERRING TO RELY ALTERNATIVELY ON AGGRESSIVE
RISK TAKING OR UNDUE CAUTION. OR AGAIN, INHERENT RISKS
MAY SIMPLY BE OPTIMISTICALLY IGNORED. IN REALITY, FAR
BETTER DECISIONS WITH HIGHER CHANCES OF PROJECT
SUCCESS ARE REACHED BY FACING THESE ISSUES.
1
2
3

## Slide 8: PMBOK FIGURE
Project Risk Management (Page 1 of 3)
Risk Management Planning
Inputs
  Project Charter
  Organization’s risk management policies
  Defined Roles and responsibilities
  Stakeholder risk tolerances
  Template for the organization’s plan
  Work breakdown structure (WBS)
Tools & Techniques
  Planning Meetings
Outputs
  Risk management plan
Risk Identification
Inputs
  Risk management plan
  Project planning outputs
  Risk categories
  Historical information
Tools & Techniques
  Documentation reviews
  Information-gathering techniques
  Checklists
  Assumptions analysis
  Diagramming techniques
Outputs
  Risks
  Triggers
  Inputs to other processes
Notes: THIS IS THE OUTLINE FOR RISK MANAGEMENT FROM THE CURRENT PMBOK (Page 128)
DO NOT NEED TO MEMORIZE THIS -- THIS IS HOW THE PMBOK STRUCTURES THE INFORMATION
NOTE: THERE IS A DIFFERENCE BETWEEN THE PMBOK METHOD FOR ORGANIZING IT AND THE RISK MANAGEMENT BOOK THAT PMI MAKES AVAILABLE.
I HAVE TRIED TO MARRY THE TWO TOGETHER AS BEST AS POSSIBLE, BECAUSE THE RISK MANAGEMENT BOOK IS A GOOD SINGLE SOURCE ON THIS TOPIC. FOR THE MOST PART, PHASES 1 & 2 ARE VERY SIMILAR BETWEEN THE TWO. PHASE 3 HAS A FEW MORE DIFFERENCES AND PHASE 4 ARE VERY DIFFERENT.
KEY POINT -- INFORMATION IS STILL VALID NO MATTER HOW IT IS ORGANIZED.

## Slide 9: PMBOK FIGURE
Project Risk Management (Page 2 of 3)
Quantitative Risk Analysis
Inputs
  Risk management plan
  Identified risks
  List of prioritized risks
  List of risks for additional analysis and management
  Historical information
  Expert judgement
  Other planning outputs
Tools & Techniques
  Interviewing
  Sensitivity analysis
  Decision tree analysis
  Simulation
Outputs
  Prioritized list of quantified risks
  Probabilistic analysis of the project
  Probability of achieving the cost and time objectives
  Trends in quantitative risk analysis results
Qualitative Risk Analysis
Inputs
  Risk management plan
  Identified risks
  Project status
  Project type
  Data precision
  Scales of probability and impact
  Assumptions
Tools & Techniques
  Risk probability and impact
  Probability/impact risk rating matrix
  Project assumptions testing
Outputs
  Overall risk ranking for the project
  List of prioritized risks
  List of risks for additional analysis and management
  Trends in qualitative risk analysis results
Notes: THIS IS THE OUTLINE FOR RISK MANAGEMENT FROM THE CURRENT PMBOK (Page 128)
DO NOT NEED TO MEMORIZE THIS -- THIS IS HOW THE PMBOK STRUCTURES THE INFORMATION
NOTE: THERE IS A DIFFERENCE BETWEEN THE PMBOK METHOD FOR ORGANIZING IT AND THE RISK MANAGEMENT BOOK THAT PMI MAKES AVAILABLE.
I HAVE TRIED TO MARRY THE TWO TOGETHER AS BEST AS POSSIBLE, BECAUSE THE RISK MANAGEMENT BOOK IS A GOOD SINGLE SOURCE ON THIS TOPIC. FOR THE MOST PART, PHASES 1 & 2 ARE VERY SIMILAR BETWEEN THE TWO. PHASE 3 HAS A FEW MORE DIFFERENCES AND PHASE 4 ARE VERY DIFFERENT.
KEY POINT -- INFORMATION IS STILL VALID NO MATTER HOW IT IS ORGANIZED.

## Slide 10: PMBOK FIGURE
Project Risk Management (Page 3 of 3)
Risk Response Planning
Inputs
  Risk management plan
  List of prioritized risks
  Risk rankings of the project
  Prioritized list of quantified risks
  Probabilistic analysis of the project
  Probability of achieving the cost and time objectives
  List of potential responses
  Risk thresholds
  Risk owners
  Common risk causes
  Trends in qualitative and quantitative risk analysis results
Risk Monitoring and Control
Inputs
  Risk management plan
  Risk response plan
  Project communication
  Additional risk identification and analysis
Tools & Techniques
  Procurement
  Contingency Planning
  Alternative Strategies
  Insurance
Outputs
  Risk Management Plan
  Inputs to other Processes
  Contingency Plans
  Reserves
  Contractual Agreements
Risk Response Planning (continued)
Tools & Techniques
  Avoidance
  Transference
  Mitigation
  Acceptance
Outputs
  Risk response plan
  Residual risks
  Secondary risks
  Contractual agreements
  Contingency reserve amounts needed
  Inputs to other processes
  Inputs to a revised project plan
Notes: THIS IS THE OUTLINE FOR RISK MANAGEMENT FROM THE CURRENT PMBOK (Page 128)
DO NOT NEED TO MEMORIZE THIS -- THIS IS HOW THE PMBOK STRUCTURES THE INFORMATION
NOTE: THERE IS A DIFFERENCE BETWEEN THE PMBOK METHOD FOR ORGANIZING IT AND THE RISK MANAGEMENT BOOK THAT PMI MAKES AVAILABLE.
I HAVE TRIED TO MARRY THE TWO TOGETHER AS BEST AS POSSIBLE, BECAUSE THE RISK MANAGEMENT BOOK IS A GOOD SINGLE SOURCE ON THIS TOPIC. FOR THE MOST PART, PHASES 1 & 2 ARE VERY SIMILAR BETWEEN THE TWO. PHASE 3 HAS A FEW MORE DIFFERENCES AND PHASE 4 ARE VERY DIFFERENT.
KEY POINT -- INFORMATION IS STILL VALID NO MATTER HOW IT IS ORGANIZED.

## Slide 11: TYPICAL RISK ITEMS

## Slide 12: TYPICAL RISK ITEMS (continued)

## Slide 13: TYPICAL RISK ITEMS (continued)

## Slide 14: Negative Risk
A dictionary definition of risk is “the possibility of loss or injury.”
Negative risk involves understanding potential problems that might occur in the project and how they might impede project success.
Negative risk management is like a form of insurance; it is an investment.

## Slide 15: Risk Can Be Positive
Positive risks are risks that result in good things happening; sometimes called opportunities.
A general definition of project risk is an uncertainty that can have a negative or positive effect on meeting project objectives.
The goal of project risk management is to minimize potential negative risks while maximizing potential positive risks.

## Slide 16: Risk Utility
Risk utility or risk tolerance is the amount of satisfaction or pleasure received from a potential payoff.
  Utility rises at a decreasing rate for people who are risk-averse.
  Those who are risk-seeking have a higher tolerance for risk and their satisfaction increases when more payoff is at stake.
  The risk-neutral approach achieves a balance between risk and payoff.

## Slide 17: Risk Utility Function and Risk Preference

## Slide 18
Upper management must ensure that project managers understand their project’s role within the context of organizational risk.
Because organizations have limited resources and many projects competing for these scarce resources, they ask project managers not to be overly optimistic in their estimates and forecasts.
Bad decisions can lead to risks that result in project delays, late finish dates, budget overruns, and unmet project goals.
Specific to firms

## Slide 19
A lack of understanding of risk on the part of management or a project manager’s wrong perceptions of management’s understanding of risks can lead to serious problems in projects.
Project managers may feel that by exposing risks they themselves may be at risk and that management may suggest more control of the risks than necessary.
A project manager’s risk tolerance depends heavily on the visibility of a project.
  A project manager may accept more risk if a project is highly visible as success will bring rewards.
  If the project is small and not that visible, taking risks may not be lucrative, and PMs may take fewer risks.
Specific to project managers

## Slide 20
Identifying and assessing risks will compel project managers to make better decisions.
While it is great to have a timeline and an agreed-upon date, risk management means that the project manager and upper management need to have realistic expectations of the people who will be doing the work.
Specific to project managers

## Slide 21
When a client and contractor lay out project goals, risk tolerances of both the client and the customer have to be defined.
Identified risks enable stakeholders of a firm to manage issues accordingly and be ready to exploit opportunities.
If a stakeholder possesses some information and does not share it with a project manager, the performance of the project will suffer as there may be risks associated with their actions.
Specific to stakeholders

## Slide 22: Project Risk Management Processes
Risk management planning: Deciding how to approach and plan the risk management activities for the project.
Risk identification: Determining which risks are likely to affect a project and documenting the characteristics of each.
Qualitative risk analysis: Prioritizing risks based on their probability and impact of occurrence.

## Slide 23: Project Risk Management Processes (cont’d)
Quantitative risk analysis: Numerically estimating the effects of risks on project objectives.
Risk response planning: Taking steps to enhance opportunities and reduce threats to meeting project objectives.
Risk monitoring and control: Monitoring identified and residual risks, identifying new risks, carrying out risk response plans, and evaluating the effectiveness of risk strategies throughout the life of the project.

## Slide 24: Risk Management Planning
The main output of risk management planning is a risk management plan—a plan that documents the procedures for managing risk throughout a project.
The project team should review project documents and understand the organization’s and the sponsor’s approaches to risk.
The level of detail will vary with the needs of the project.

## Slide 25: Topics Addressed in a Risk Management Plan
Methodology
Roles and responsibilities
Budget and schedule
Risk categories
Risk probability and impact
Risk documentation

## Slide 26: Contingency and Fallback Plans, Contingency Reserves
Contingency plans are predefined actions that the project team will take if an identified risk event occurs.
Fallback plans are developed for risks that have a high impact on meeting project objectives, and are put into effect if attempts to reduce the risk are not effective.
Contingency reserves or allowances are provisions held by the project sponsor or organization to reduce the risk of cost or schedule overruns to an acceptable level.

## Slide 27: Broad Categories of Risk
Market risk
Financial risk
Technology risk
People risk
Structure/process risk